## Feuil1
Type | Action |  | FRONT | explain | BACK | explain | GENERAL
GENERAL
| LOGIN | +google | DONE |  | DONE |  | DONE
| REGISTER | +google | DONE |  | DONE |  | DONE
| HOMEPAGE |  | IN PROGRESS | Some of the button design is missing. | DONE
| ZOOM METTING |  | IN PROGRESS | The connection to the api works, it just lacks to connect with the appointments. | DONE
| Take A Metting |  | DONE |  | IN PROGRESS
| Payment |  | NOT STARTED |  | NOT STARTED |  | NOT STARTED
| Change Picture |  | IN PROGRESS |  | DONE |  | IN PROGRESS
USER
LAWYER | Select a category |  | DONE |  | DONE |  | DONE
| see all lawyers in the category |  | DONE |  | DONE |  | DONE
| Show lawyer info |  | DONE |  | DONE |  | DONE
| Update Lawyer info |  | DONE |  | DONE |  | DONE
| View ALL meeting |  | DONE |  | IN PROGRESS | Appointment bookings are missing.
| Select availability |  | DONE |  | NOT STARTED
| Dashbord |  | NOT STARTED |  | NOT STARTED
SERVER | Firewall |  | DONE |  | DONE |  | DONE
| Databasing |  | DONE |  | DONE |  | DONE
| Pipeline front |  | DONE |  | DONE |  | DONE
| Pipeline back |  | DONE |  | DONE |  | DONE
| User rights |  | DONE |  | DONE |  | DONE